## Sheet1
Date | Hours | Notes | Links | TODO
2024-04-25 | 1.5 | Daniel setting me up
2024-04-30 | 0.5 | First meeting with Irene to talk over project
2024-05-02 | 5 | trying out xgboosted model
2024-05-03 | 5
2024-05-05 | 2
2024-05-06 | 7
2024-05-07 | 7 | meeting, trying to format data
2024-05-08 | 8 | more data formatting, finished framework for building studentgrades df
2024-05-09 | 4 | fixed bugs
2024-05-10 | 6 | adding majors and minors to studentgrades, combined majors now work
2024-05-13 | 6 | finished and pushed student major/minor, need to ask about other options… Now it’s time to find and fix bugs of empty columns…
2024-05-14 | 8 | trying out random forests, missForest, and GBM
2024-05-15 | 8 | removed all "future" courses (aka retries at the same course AND courses of a higher year level) |  | compare relevancies between courses¦ create a multi output regression model
2024-05-16 | 6 | added prediction metrics
2024-05-17 | 6 | Confusion matrix only useful for prediction, |  | Look into other and all metrics, the potential of RF's again
2024-05-18 | 1 | Adding in BA student to widen the model training pool