## Sheet1
Date | Hours | Notes | Links | TODO
2024-04-25 | 1.5 | Daniel setting me up
2024-04-30 | 0.5 | First meeting with Irene to talk over project
2024-05-02 | 5 | trying out xgboosted model
2024-05-03 | 5
2024-05-05 | 2
2024-05-06 | 7
2024-05-07 | 7 | meeting, trying to format data
2024-05-08 | 8 | more data formatting, finished framework for building studentgrades df
2024-05-09 | 4 | fixed bugs
2024-05-10 | 6 | adding majors and minors to studentgrades, combined majors now work
2024-05-13 | 6 | finished and pushed student major/minor, need to ask about other options… Now it’s time to find and fix bugs of empty columns…
2024-05-14 | 8 | trying out random forests, missForest, and GBM
2024-05-15 | 8 | removed all "future" courses (aka retries at the same course AND courses of a higher year level) |  | compare relevancies between courses¦ create a multi output regression model
2024-05-16 | 6 | added prediction metrics
2024-05-17 | 6 | Confusion matrix only useful for prediction, |  | Look into other and all metrics, the potential of RF's again
2024-05-18 | 2 | Adding in BA student to widen the model training pool (reversed..)
2024-05-19 | 4 | Creating a new dataframe to save only newest grades student recieves, weights are based on rows in GBM |  | Look into best grade student receives
2024-05-21 | 8 | Work meeting, looking into many new papers and models (matrix factorization)
2024-05-22 | 6 | Researching NMF as a method of grade estimation… cant handle NA's so nope. Now trying normal MF on STAT230 and its pre-reqs | https://modernscholarship.org/docs/2-2-PredSRMF.pdf
2024-05-23 | 7 | MF working, similar mse, need to format new dataframe to train and test with
2024-05-24 | 7 | Finished mf using recosystem, not very good.. Looking to optimize. Workday banking setup and courses.
2024-05-26 | 3 | Workday courses and minor testing |  | Changing course, no MF, at least not reguarly. Back to the drawing board.